## Actual
| Person | Day | Hours | Commit msg
Start of Sprint 1 | Riley | 2025-08-26 | 0.75 | add classes for cells and grid, including helpers
| Riley | 2025-08-28 | 0.25 | Add adjacent bomb logic
| Dustin | 2025-08-28 | 0.2 | creating the readme and github directory files
| Dustin | 2025-08-28 | 0.1 | Create different folders names and github contents with separate branches
| Colin | 2025-08-28 | 1 | Render 10x10 grid with a border
| Dustin | 2025-08-29 | 0.3 | creating draft system architecture /estimated project time hours documents
| Hannah | 2025-08-28 | 3 | Created the algorithms
| Ryland | 2025-08-28 | 0.5 | added unrevealed tile
| Jacob | 2025-08-28 | 1.15 | Research Minesweeper games, learn rules, gather UI inspiration, browse images/themes
Start of Sprint 2 | Dustin | 2025-09-04 | 1.1 | creating button clicker function files (rough draft--will be merged later)
| Riley | 2025-09-02 | 0.5 | Make some bomb logic more robust
| Riley | 2025-09-05 | 0.5 | Add grid logic
| Hannah | 2025-09-07 | 2 | Created architecture documents and diagrams
| Ryland | 2025-09-07 | 0.2 | added revealed tile
| Ryland | 2025-09-08 | 0.5 | added tile 1 thru 6
| Ryland | 2025-09-08 | 0.2 | added 7 and 8 tile
| Riley | 2025-09-08 | 0.5 | Improve reveal logic and add wave and flags
| Riley | 2025-09-08 | 0.1 | Add image updates for numbers
| Colin | 2025-09-02 | 0.6 | add a start page and add option to select number of bombs
| Colin | 2025-09-09 | 0.4 | add end page
| Ryland | 2025-09-09 | 0.1 | added flag tile
| Jacob | 2025-09-09 | 1.5 | Built header prototype: setup Pygame window, loaded/scaled nautical assets, added buoy counter and timer text
Sprint 3 | Dustin | 2025-09-12 | 0.6 | enhance the button clicker files!
| Colin | 2025-09-09 | 0.4 | Change font and add labels to columns and rows
| Hannah | 2025-09-12 | 0.5 | work on merging with dev/riley branch
| Dustin | 2025-09-12 | 0.9 | start writing project documentations
| Colin | 2025-09-12 | 1.5 | work on merging with dev/riley branch
| Riley | 2025-09-12 | 1 | work on merging with dev/riley branch
| Riley | 2025-09-15 | 0.1 | refix cell position on reveal
| Hannah | 2025-09-14 | 1 | Create win lose algorithms
| Ryland | 2025-09-14 | 0.8 | added windows vs mac compatiblity
| Ryland | 2025-09-15 | 0.5 | added mine and flag imgs for header
| Jacob | 2025-09-15 | 2 | Integrated header with grid: aligned dimensions, ensured assets scaled with display size
Sprint 4 | Riley | 2025-09-16 | 0.25 | Merge into main branch
| Dustin | 2025-09-16 | 0.2 | check header comments / add comment to header.py
| Dustin | 2025-09-17 | 0.3 | clean up readme !
| Hannah | 2025-09-17 | 1 | edit the system architecture documentation
| Riley | 2025-09-18 | 1 | fix/merge header and add stop timer
| Ryland | 2025-09-18 | 0.5 | added win screen picture
| Ryland | 2025-09-18 | 0.5 | added lose screen picture
| Colin | 2025-09-18 | 0.5 | test final product
| Jacob | 2025-09-17 | 1.5 | Debugged header–grid integration issue causing click events to fail; documented findings before teammate implemented fix
| Jacob | 2025-09-18 | 0.75 | Added flashing "NOW PLAYING" status text to header and tested gameplay to verify full system functionality
| Ryland | 2025-09-18 | 0.5 | cleaned up textures, moved assets into textures
| Riley | 2025-09-19 | 0.25 | Add now playing indicator and remove debug print

## Estimate
Start of Sprint 1
Name | Task | Estimate (hours)
Riley | Make grid and cell classes | 1
Colin | Render 10 x 10 grid in main page | 1 | Methodology: We used expert evaluation to do this because we were all very familar with the systems we were using and what we needed to do.
Dustin | Start making a plan of required docs / locations | 1
Hannah | Make the flood fill and place bombs functions | 2
Ryland | Make all different tile images | 2
Jacob | Research Minesweeper games, learn rules, gather UI inspiration, browse images/themes | 1
Start of Sprint 2
Name | Task | Estimate
Riley | Integrate UI with grid and cell | 1.5
Colin | Create start page with option for user to select number of bombs | 0.5
Dustin | make button functions | 1.5
Hannah | Create diagrams and start system architecture documentation | 1.5
Ryland | complete tiles | 0.5
Jacob | Built header prototype: setup Pygame window, loaded/scaled nautical assets, added buoy counter and timer text | 2
Start of Sprint 3
Colin | Create end page | 0.4
Colin | Change font and add labels to columns and rows | 0.5
Colin | Merge with Riley branch | 1
Hannah | Create the win/lose algorithm | 1
Riley
Ryland | add win and lose backgrounds | 0.5
Jacob | Integrated header with grid: aligned dimensions, ensured assets scaled with display size | 1.5
Dustin | Start creating and further depth the system documents | 0.5
Start of Sprint 4
Riley | Update documentation, help integrate header, fix some known bugs | 1
Hannah | Finalize the system architecture documentation, test and help debug | 2
Ryland | clean up files and QA testing | 0.8
Colin | Test the final product to confirm everything works | 0.5
Jacob | Debugged header–grid integration issue causing click events to fail; documented findings before teammate implemented fix | 1
Jacob | Added flashing "NOW PLAYING" status text to header and tested gameplay to verify full system functionality | 1
Dustin | Finalize the readme docs | 0.2